## Role_to_task_jalons
Task_ID | Step_No | Module | Task | milestones | Role_ID column | Role | dispatch_date
1 | 1 |  | Management Decision | yes | 2/5/6/7 | Management | 700
2 | 2 |  | Paediatric Investigation Plan (PIP) |  | 1/2/3/4/6 | Global Regulatory Lead | 700
3 | 2 |  | Paediatric Investigation Plan (PIP) agreed | yes | EMA |  | 700
3 | 3 |  | General Kick-off meeting | yes | 1/2/3/4/6/7 | Global Regulatory Lead | 600
4 | 4 |  | Content Plan (documents list) prepared |  | 1/2/3/4/6/7 | Regulatory Strategist (Global/EU) | 180
5 | 5 |  | Scientific advice / end of phase 2 meeting | yes | 1/2/3/4/6/7 | Global Regulatory Lead | 550
6 | 6 |  | Target Product Profile finalized (TPP) |  | 1/2/3/4/5/6/7 | Global Regulatory Lead | 400
7 | 7 |  | Centralised Procedure Eligibility Request |  | 1/2/3/4/7 | Regulatory Strategist (Global/EU) | 130
8 | 8 |  | Letter of Intent sent to EMA | yes | 1/2/3/ | Regulatory Strategist (Global/EU) | 210
9 | 9 |  | Preparation of the pre-submission meeting with Rapporteurs |  | 1/2/3/4/6/7 | Regulatory Strategist (Global/EU) | 180
10 | 10 |  | Pre-submission meeting with Rapporteurs Request |  | 1/2/3/4/7 | Regulatory Strategist (Global/EU) | 185
11 | 11 |  | EMA pre-submission meeting | yes | 1/2/3/4/6/7 | Regulatory Strategist (Global/EU) | 90
12 | 12 |  | Orphan Drug Designation granted |  | 1/2/3/4/6/7 | Global Regulatory Lead | 700
13 | 13 |  | Invented name approval (EMA NRG) |  | 1/2/3/4/6 | Regulatory Operations | 300
14 | 14 |  | IDMP data readiness |  | 1/2/3/4/7 | Regulatory Operations | 180
15 | 15 |  | ATC code request |  | 1/2/3/ | Regulatory Operations | 300
16 | 16 | Module 4 | Final nonclinical pharmacology study report | yes | 6/ | Regulatory Strategist (Global/EU) | 450
17 | 17 | Module 5 | Final toxicokinetic/pharmacokinetic study report | yes | 6/ | Regulatory Operations | 450
18 | 18 | Module 5 | Final toxicology study report | yes | 6/ | Regulatory Operations | 450
19 | 19 | Module 5 | Final clinical study report (last pivotal study) | yes | 6/ | Regulatory Strategist (Global/EU) | 450
20 | 20 | Module 5 | Final Population PK analysis report | yes | 6/ | Regulatory Operations | 450
21 | 21 | Module 5 | Integrated Summary of Safety (ISS) |  | 1/2/3/4/6 | Regulatory Operations | 400
22 | 22 | Module 5 | Integrated Summary of Efficacy (ISE) |  | 1/2/3/4/6 | Regulatory Operations | 400
23 | 23 | Module 5 | Integrated Summary of Immunogenicity |  | 1/2/3/4/6 | Regulatory Operations | 400
24 | 24 | Module 2 | Summary of Biopharmaceutic Studies (Module 2.7.1) |  | 1/2/3/4/6 | Regulatory Strategist (Global/EU) | 400
25 | 25 | Module 2 | Summary of Clinical Pharmacology (Module 2.7.2) |  | 1/2/3/4/6 | Regulatory Strategist (Global/EU) | 400
26 | 26 | Module 2 | Summary of Clinical Efficacy (Module 2.7.3) |  | 1/2/3/4/6 | Regulatory Strategist (Global/EU) | 400
27 | 27 | Module 2 | Summary of Clinical Safety (Module 2.7.4) |  | 1/2/3/4/6 | Regulatory Strategist (Global/EU) | 400
28 | 28 | Module 2 | Clinical Overview (Module 2.5) |  | 1/2/3/4/6 | Regulatory Strategist (Global/EU) | 400
29 | 29 |  | Clinical literature references compiled (Module 2.7.5) |  |  | Labeling | 400
30 | 30 | Module 5 | Clinical literature references (Module 2.7.5) |  | 1/2/3/4/6 | Regulatory Strategist (Global/EU) | 400
31 | 31 | Module 5 | Clinical study synopses (Module 2.7.6) |  | 1/2/3/4/6 | Regulatory Strategist (Global/EU) | 400
32 | 32 | Module 2 | Nonclinical Introduction (Module 2.6.1) |  | 1/2/3/6 | Regulatory Strategist (Global/EU) | 400
33 | 33 | Module 2 | Nonclinical Written Summary â€“ Pharmacology (Module 2.6.2) |  | 1/2/3/6 | Regulatory Strategist (Global/EU) | 400
34 | 34 | Module 2 | Nonclinical Tabulated Summary â€“ Pharmacology (Module 2.6.3) |  | 1/2/3/6 | Regulatory Strategist (Global/EU) | 400
35 | 35 | Module 2 | Nonclinical Written Summary â€“ Pharmacokinetics (Module 2.6.4) |  | 1/2/3/6 | Regulatory Strategist (Global/EU) | 400
36 | 36 | Module 2 | Nonclinical Tabulated Summary â€“ Pharmacokinetics (Module 2.6.5) |  | 1/2/3/6 | Regulatory Strategist (Global/EU) | 400
37 | 37 | Module 2 | Nonclinical Written Summary â€“ Toxicology (Module 2.6.6) |  | 1/2/3/6 | Regulatory Strategist (Global/EU) | 400
38 | 38 | Module 2 | Nonclinical Tabulated Summary â€“ Toxicology (Module 2.6.7) |  | 1/2/3/6 | Regulatory Strategist (Global/EU) | 400
39 | 39 | Module 2 | Nonclinical Overview (Module 2.4) |  | 1/2/3/6 | Regulatory Strategist (Global/EU) | 400
40 | 40 | Module 4 | Nonclinical literature references (Module 4.3) |  | 1/2/3/6 | Regulatory Strategist (Global/EU) | 450
41 | 41 |  | GMP Clearance (for manufacturing sites) |  | 1/3/6/7 | Regulatory Operations | 150
42 | 42 |  | GMP Certificates (from manufacturing sites) |  | 1/3/6/7 | Regulatory Operations | 150
43 | 43 |  | Manufacturing Authorisations |  | 1/3/6/7 | Regulatory Operations | 150
44 | 44 |  | Manufacturing Process Flow Chart |  | 1/3/6/7 | Regulatory Operations | 450
45 | 45 | Module 3 | 3.2.S.1 Drug Substance: General Information section |  | 1/3/4/6/7 | Regulatory Operations | 450
46 | 46 | Module 3 | 3.2.S.2 Drug Substance: Manufacture section |  | 1/3/4/6/7 | Regulatory Operations | 450
47 | 47 | Module 3 | 3.2.S.3 Drug Substance: Characterisation section |  | 1/3/4/6/7 | Regulatory Operations | 450
48 | 48 | Module 3 | 3.2.S.4 Drug Substance: Control of Drug Substance section |  | 1/3/4/6/7 | Regulatory Operations | 450
49 | 49 | Module 3 | 3.2.S.5 Drug Substance: Reference Standards section |  | 1/3/4/6/7 | Regulatory Operations | 450
50 | 50 | Module 3 | 3.2.S.6 Drug Substance: Container Closure System section |  | 1/3/4/6/7 | Regulatory Operations | 450
51 | 51 | Module 3 | 3.2.S.7 Drug Substance: Stability section |  | 1/3/4/6/7 | Regulatory Operations | 450
52 | 52 | Module 3 | 3.2.P.1 Drug Product: Description and Composition section |  | 1/3/4/6/7 | Regulatory Operations | 450
53 | 53 | Module 3 | 3.2.P.2 Drug Product: Pharmaceutical Development section |  | 1/3/4/6/7 | Regulatory Operations | 450
54 | 54 | Module 3 | 3.2.P.3 Drug Product: Manufacture section |  | 1/3/4/6/7 | Regulatory Operations | 450
55 | 55 | Module 3 | 3.2.P.4 Drug Product: Control of Excipients section |  | 1/3/4/6/7 | Regulatory Operations | 450
56 | 56 | Module 3 | 3.2.P.5 Drug Product: Control of Drug Product section |  | 1/3/4/6/7 | Regulatory Operations | 450
57 | 57 | Module 3 | 3.2.P.6 Drug Product: Reference Standards section |  | 1/3/4/6/7 | Regulatory Operations | 450
58 | 58 | Module 3 | 3.2.P.7 Drug Product: Container Closure System section |  | 1/3/4/6/7 | Regulatory Operations | 450
59 | 59 | Module 3 | 3.2.P.8 Drug Product: Stability section |  | 1/3/4/6/7 | Regulatory Operations | 450
60 | 60 | Module 3 | 3.2.A.1 Appendices: Facilities and Equipment |  | 1/3/4/6/7 | Regulatory Operations | 450
61 | 61 | Module 3 | 3.2.A.2 Appendices: Adventitious Agents Safety |  | 1/3/4/6/7 | Regulatory Operations | 450
62 | 62 | Module 3 | 3.2.R Regional Information section completed |  | 1/3/4/6/7 | Regulatory Operations | 450
63 | 63 | Module 2 | Quality Overall Summary â€“ Introduction (Module 2.3.1) |  | 1/3/4/6/7 | Regulatory Strategist (Global/EU) | 400
64 | 64 | Module 2 | Quality Overall Summary â€“ Drug Substance (Module 2.3.S) |  | 1/3/4/6/7 | Regulatory Strategist (Global/EU) | 400
65 | 65 | Module 2 | Quality Overall Summary â€“ Drug Product (Module 2.3.P) |  | 1/3/4/6/7 | Regulatory Strategist (Global/EU) | 400
66 | 66 | Module 2 | Quality Overall Summary â€“ Appendices (Module 2.3.A) |  | 1/3/4/6/7 | Regulatory Strategist (Global/EU) | 400
67 | 67 | Module 2 | Quality Overall Summary â€“ Regional Information (Module 2.3.R) |  | 1/3/4/6/7 | Regulatory Strategist (Global/EU) | 400
68 | 68 |  | Company Core Data Sheet (CCDS) |  | 1/2/3/4/6/7 | Regulatory Operations | 700
69 | 69 |  | Risk Management Plan (RMP) |  | 1/3/4/6/ | Regulatory Strategist (Global/EU) | 150
70 | 70 |  | EU SmPC (Product Information) |  | 2/3/4/7 | Regulatory Strategist (Global/EU) | 150
71 | 71 |  | Messaging alignment meeting 1 | yes | 2/3/4/6/7 | Regulatory Operations | 420
72 | 72 |  | Messaging alignment meeting 2 | yes | 1/2/3/4/6/7 | Regulatory Operations | 300
73 | 73 |  | Application Form (eAF) |  | 3/4/7/ | Regulatory Strategist (Global/EU) | 180
74 | 74 |  | Cover Letter for MAA submission |  | 1/3/ | Regulatory Operations | 180
75 | 75 |  | Product Artwork and Mock-ups |  | 3/4/6/7 | Regulatory Operations | 130
76 | 76 |  | Compilation of eCTD dossier |  | 1/ | Regulatory Strategist (Global/EU) | 130
77 | 77 |  | Final internal review and sign-off |  | 2/3/4/6/7 | Regulatory Operations | 10
78 | 78 |  | Validation of dispatch of MAA to EMA |  | EMA | Regulatory Operations | -5 | Cette tâche vient après Dispatch of MAA to EMA et avant le EMA confirmation of submission receipt
79 | 79 |  | Dispatch of MAA to EMA | yes | 1/ | Regulatory Operations | 0
80 | 80 |  | EMA confirmation of submission receipt | yes | EMA | Regulatory Operations | -21